## Start Here
Burton Inn: permitting and licensing workbook
24007 Vashon Hwy SW, Vashon, WA 98070 (unincorporated King County). Built Oct 13, 2026 from the research task.
Key numbers
| Low | High
Rooms only: weeks until first guest can book | 3 | 8 | From the Rooms Only tab. Set its scenario switch to include the occupancy-review add-on.
Rooms only: one-time cost, known items ($) | 150 | 650 | Excludes items with no number yet; see Costs.
Kitchen and liquor: weeks to open | 24 | 32 | From the Critical Path tab; assumes the septic does not need a major redesign.
Kitchen and liquor: one-time cost ($) | 28364 | 308200 | Septic upgrade is the wild card (zero to $150,000).
Permit tracker (from Master List)
Open | 20
In progress | 0
Done | 0
N/A | 0
What to know first
The kitchen, not the liquor license, is the critical path. It has been closed more than 365 days, so Public Health requires a full plan review.
Burton is almost certainly on septic. Grease handling and septic capacity are the likeliest deal-breakers for the restaurant.
The roofless Type I hood needs King County mechanical and fire suppression permits before Public Health will do its preoperational inspection.
The liquor license takes 60 to 90 days and runs in parallel. File about 90 days before the target open date.
The rooms do not depend on any of that. Their gate is the zoning letter and the lease check.
No true stopgap liquor license exists for a for-profit business. Special Occasion licenses are for nonprofits only.
Caveats
Zoning, septic status, water provider and landmark status come from secondary sources and are not confirmed against official King County records. Treat them as leads.
Cost ranges marked estimate are planning figures, not quotes. Fees marked 'per 2026 schedule' were not retrieved.
The 2024 building codes take effect May 3, 2027. Rules after that date may differ.
This is not legal advice. Confirm with LCB, King County DLS and Public Health.
Legend
Blue text on yellow | Cells you edit: status, start weeks, include switches, assumptions.
Green text | Pulled from another tab.
Black text | Formulas and research findings. Leave alone.
Tabs
Rooms Only | Fastest path: just the 4 upstairs rooms
Master List | All 20 permits and licenses with status
Alcohol Paths | License types compared, partner's mobile bar, structure options
Lodging | R-1 vs R-3 vs B&B vs 30+ day
Kitchen | Reactivation checklist
Critical Path | Week-by-week chart for kitchen and liquor
Costs | Low and high estimates with totals
Open Questions | Records to request and decisions to make
Sources | Every link with a reliability flag

## Rooms Only
Rooms only: opening the 4 upstairs rooms as short-term rentals
No kitchen, septic or liquor license needed for this path. Weeks are counted from today. Blue on yellow cells are yours to edit.
# | Task | Who | Depends on | Start low (wk) | Start high (wk) | Duration low (wk) | Duration high (wk) | End low (wk) | End high (wk) | Fee | Status | Notes
1 | Request permit history and Certificate of Occupancy (1993 permit, occupancy class, expired permits, code enforcement) | Owner | None | 0 | 0 | 2 | 6 | 2 | 6 | Copy fees only | Open | King County Permitting Records Center. Informs the occupancy risk row below. Not a hard gate for go-live.
2 | Zoning and Historical Certification Letter; confirm lodging use is allowed and read the P-suffix text | Owner / architect | None | 0 | 0 | 2 | 6 | 2 | 6 | Per KC 2026 fee schedule | Open | THE gate. Zoning is probably NB-P but unconfirmed. If a B&B guesthouse needs a resident operator, the plan changes.
3 | Confirm the lease allows nightly lodging; get landlord consent in writing | Owner | None | 0 | 0 | 1 | 2 | 1 | 2 | None | Open | Do this before spending money on anything else.
4 | WA business license for Burton Inn LLC; register for lodging and sales tax | Owner | None | 0 | 0 | 1 | 3 | 1 | 3 | $50 application fee | Open | DOR Business Licensing Service. Airbnb collects most lodging taxes but you still file returns.
5 | Liability insurance ($1M or equivalent platform coverage) and RCW 64.37 postings (safety and contact info) | Owner | None | 0 | 0 | 1 | 2 | 1 | 2 | Premium: get a quote | Open | State short-term rental law. Check that the policy covers nightly rentals of a commercial building.
6 | Smoke and CO alarm check in every room and the egress path; set guest cap (10 vs 16) | Owner / contractor | Task 3 | 1 | 2 | 1 | 2 | 2 | 4 | Alarms: see Costs | Open | Cap of 10 guests total likely keeps the rooms in the cheaper R-3 category. 16 means R-1.
7 | Listing setup: photos, house rules, tax collection settings | Owner | Task 2 | 2 | 6 | 1 | 2 | 3 | 8 | None | Open | Do not publish before the zoning answer is in hand.
8 | GO LIVE: all of the above complete |  | Tasks 2 to 7 | 3 | 8 | 0 | 0 | 3 | 8 |  | Open | Earliest and latest week the first guest can book, if no occupancy surprise turns up.
| Scenarios | [6 empty] | Low (wk) | High (wk)
| Base case: first guest can book | [6 empty] | 3 | 8
| Add-on if records show no lodging occupancy history, so a change of occupancy review is needed (my estimate, weeks) | [6 empty] | 8 | 24
| Include the add-on? 1 = yes, 0 = no | [6 empty] | 0
| Go-live with the selected scenario | [6 empty] | 3 | 8
Decisions only you can make
Guest cap: 10 total (likely R-3, cheaper) or up to 16 (R-1, more revenue, more fire and egress scrutiny).
Whether you or an on-site manager will live in the building. A bed and breakfast guesthouse classification may require a resident operator (secondary source, verify).
Accessibility: rooms are upstairs only. Repairs alone do not trigger upgrades, but document a feasibility note in case the county asks.

## Master List
Master permit and license list
20 items from the research. Fees and times marked (est.) are planning estimates. Status is yours to edit.
# | Item | Applies to | Needed for rooms only? | Agency / portal | Fee (source) | Typical time | Prerequisites | Who | Status | Notes
1 | Records requests: permits, CO, code enforcement, OSS as-built, PH inspections, LCB history | Both | Yes | KC Permitting Records Center; PHSKC; LCB Public Records | Copy fees only (est.) | 2 to 6 wks | None | Owner | Open
2 | Zoning and Historical Certification Letter / pre-application meeting | Both | Yes | KC DLS via MyBuildingPermit.com | Per 2026 KC fee schedule (2025 fees rose 49%) | 2 to 6 wks (est.) | Parcel number | Owner / architect | Open | Confirms NB-P zoning, P-suffix text, and whether lodging and restaurant uses are allowed.
3 | WA business license, UBI, trade name | Both | Yes | DOR Business Licensing Service | $50 application handling fee (WAC 458-02-200) | 1 to 3 wks | LLC formed | Owner | Open
4 | Septic evaluation by certified On-site System Maintainer | Kitchen | No | Private OSM; report to PHSKC | $500 to $1,500 (est.) | 1 to 3 wks | OSS as-built | Owner | Open | Burton is almost certainly on septic, not the Vashon Sewer District.
5 | OSS design or modification, grease interceptor | Kitchen | No | PHSKC OSS program plus licensed designer | Fee schedule BOH 2.18; design $3k to $10k (est.) | 6 to 16 wks (est.) | Septic evaluation | Designer / installer | Open | Biggest swing factor in cost and time.
6 | Water service and backflow confirmation | Kitchen | No | Burton Water Co-op (verify) | Unknown | 1 to 4 wks | None | Owner / plumber | Open
7 | Food plan review (full, because closed more than 365 days) | Kitchen | No | PHSKC Permit Center | $1,008 base + $252 per extra hour (PHSKC 2026) | About 2 to 8 wks | Menu, equipment plan, septic direction | Owner / designer | Open
8 | Mechanical permit: Type I hood, roof fan, makeup air | Kitchen | No | KC DLS | Per 2026 fee schedule | 3 to 10 wks (est.) | Hood engineering | Mechanical contractor | Open | Roof fan was removed. With no documents, assume listing, duct and suppression need recertifying.
9 | Fire suppression (UL 300) permit and test | Kitchen | No | KC Fire Marshal | Per 2026 fee schedule | 2 to 6 wks (est.) | Hood design | Fire contractor | Open
10 | Electrical permit | Kitchen | No | WA L&I (inferred) | Per L&I schedule | Days to 2 wks | None | Electrician | Open
11 | Plumbing permit: sinks, interceptor | Kitchen | No | PHSKC plumbing (inferred) | Per PHSKC schedule | 1 to 3 wks | Food plan review | Plumber | Open
12 | Building permit, only if any alteration goes beyond repair | Both | If needed | KC DLS | Per 2026 fee schedule | 4 to 16 wks (est.) | Zoning letter, mechanical | Architect | Open | Conditional.
13 | Final inspections and CO confirmation | Both | If needed | KC DLS; Fire Marshal | Included | 1 to 3 wks | Trade permits closed | Contractor | Open
14 | PH preoperational inspection and annual operating permit | Kitchen | No | PHSKC | $756 (Risk 2) or $1,008 (Risk 3), 13 to 50 seats | 1 to 2 wks after finals | Plan review, finals | Owner | Open | Risk level depends on the menu.
15 | LCB liquor license | Alcohol | No | LCB via DOR Business Licensing Service | $600 (beer/wine) or $2,200 to $2,700 (spirits, beer and wine) a year | 60 to 90 days | Business license, lease, floor plan | Owner | Open | File about 90 days before the target open date.
16 | MAST permits (Class 12 or 13) for every server | Alcohol | No | LCB-certified trainers | Trainer fee (verify) | 1 day | Hire | Staff | Open
17 | Food worker cards; Certified Food Protection Manager | Kitchen | No | WA DOH online; ANSI exam | Card fee (verify) | 1 day | None | Staff | Open | CFPM expectation not verified.
18 | Short-term rental compliance: RCW 64.37 insurance and postings | Rooms | Yes | Self / insurer | Premium | 1 to 2 wks | Zoning letter | Owner | Open
19 | Fire operational permits and annual inspection | Kitchen | No | KC Fire Marshal | Not published by VIFR; KC schedule | Annual | Finals | Owner | Open | Unincorporated Vashon falls under the King County Fire Marshal.
20 | Sign permit | Both | No | KC DLS (KCC 21A.20.095) | Per 2026 schedule | 2 to 6 wks | Zoning letter | Sign company | Open | Optional.

## Alcohol Paths
Alcohol license paths (on-premise only)
Fees are LCB 2026 annual figures from the research. Fit column is my read, not LCB's.
Path | Eligibility and food rules | Privileges | Limits | Annual fee | Fit for Burton Inn
1. Spirits, Beer and Wine Restaurant | Bona fide restaurant: 4 complete meals cooked on site, cook on duty, menu, kitchen equipment (WAC 314-02-035). Under 100% dining: complete meals at least 5 hrs a day, 3 days a week, between 8 a.m. and 11 p.m. | Full bar; catering endorsement ($525); premixed cocktails to go with a meal; off-premises wine ($180) | Hood and full kitchen must be live; meal records required | $2,200 (50%+ dining), $2,700 (under 50%), $1,400 (service bar) | Best if a real menu is planned
2. Beer and/or Wine Restaurant | Minimum food service (sandwiches, soup, pizza, etc.) | Beer and wine on tap or opened; catering, off-premises and wine-to-go endorsements | No spirits | $300 beer, $300 wine, $600 both | Lowest-risk start; can upgrade later
3. Beer and/or Wine Tavern | No food requirement listed | Beer and wine on premises; catering endorsement | No one under 21 on premises at any time | $300 / $300 / $600 | Poor fit for an inn and family dining
4. Snack Bar | Snack food; designated seating | Beer by opened bottle or can, wine by the glass | No taps; beer cannot be the principal business | $187.50 | Possible if the kitchen is delayed
5. Catering endorsement | Needs an underlying restaurant or tavern license | Serve at unlicensed off-site events | Not at other licensed premises | $525 | Lets the Inn do off-site events, separate from the partner
6. Special Occasion / banquet | Special Occasion: bona fide nonprofits only, 12 single-day events a year. Banquet: invitation only, no charge for liquor | Short events | Retail licensees cannot get banquet permits; no third-party promoter cut on Special Occasion | $90 a day; $25 a day | Only a nonprofit-hosted bridge. No real stopgap for a for-profit.
7. Hotel / Motel | Hotel requires 20+ rooms. Motel license allows honor bars in up to 50% of rooms | In-room alcohol | 4 rooms fails the hotel test; motel eligibility unverified | $2,500 / $750 | Likely not available
Partner's mobile bar
LCB liquor caterer licenses are prohibited from catering events at liquor-licensed premises. Once the Inn is licensed, the partner's separate business cannot pour at the Inn under its own license. Partner staff can work Inn events as Burton Inn LLC employees with MAST permits, using the Inn's inventory.
Structure options
(a) Burton Inn LLC holds the license and operates | Simplest. The lease must allow it.
(b) Operator (partner's company) subleases the kitchen and bar and holds the license | Operator needs its own lease or sublease, UBI and Public Health permit. Burton Inn LLC cannot share in alcohol revenue without being disclosed.
(c) Management agreement with Burton Inn LLC as licensee | Must be disclosed to and reviewed by LCB.
Alcohol in the guest rooms
A restaurant license covers only the floor-plan premises. Welcome bottles bundled into a paid stay are a likely unlicensed sale. Do not do it without written LCB guidance.
LCB process
Step 1 | File through DOR Business Licensing Service no more than 90 days before opening (needs a business address).
Step 2 | Licensing specialist contacts you within about a week. Phase 1 takes about 10 days.
Step 3 | LCB notifies King County, which has 20 days to respond (60 in an Alcohol Impact Area; Burton is not one, verify).
Step 4 | Public notice posted at the premises for 14 days.
Step 5 | You submit business structure, financing sources, lease and floor plan. Principals are fingerprinted.
Step 6 | On approval, an approval letter acts as a 30-day license until the business license with liquor endorsement arrives. Typical total: 60 to 90 days.

## Lodging
Lodging classification comparison (4 upstairs rooms)
Occupancy classes are inferred from the 2021 IBC; confirm against the 1993 permit and Certificate of Occupancy.
Path | Code occupancy | Zoning use | Guests | Key trade-off
Inn rooms, up to 16 guests | R-1 | Hotel/motel or B&B (verify in NB zone) | 16 | Most revenue; highest fire and egress scrutiny
Transient lodging house, 10 guests or fewer | R-3 (5 or fewer rooms, 10 or fewer occupants) | Same as above | 10 | Cheapest code path
B&B guesthouse | R-3 likely | B&B guesthouse (5 rooms or fewer; residency condition reported by one secondary source) | 10 | Needs a resident operator if that condition is confirmed
30+ day rentals | R-2 or R-3 | Residential per NB rules |  | Avoids short-term rental taxes; tenant law applies
Other points
Washington RCW 64.37 defines a short-term rental as lodging that is not a hotel, motel or bed and breakfast, and excludes a duly licensed inn or hotel. Unincorporated King County has no dedicated STR permit program (secondary sources; verify).
Parking (KCC 21A.18): B&B guesthouse needs 1 space per guest room plus 2 per facility (6 total for 4 rooms). Hotel/motel needs 1 per bedroom. The restaurant adds its own requirement.
Downstairs: a 40-seat dining room with an occupant load under 50 is generally Group B. Fifty or more makes it A-2, which raises egress and fire alarm demands.
Accessibility: repairs do not trigger upgrades. Alterations to primary-function areas can, with a 20% disproportionate-cost cap and technical infeasibility exceptions. The federal ADA lodging exemption likely does not apply unless the proprietor lives on site.
Codes: 2021 codes apply now. The 2024 codes take effect May 3, 2027; permits applied for before then should be reviewed under the 2021 codes.

## Kitchen
Kitchen reactivation checklist
Assumes no equipment documents survive. Status is yours to edit.
# | Area | What to do | Who | Status
1 | Equipment inventory | List every remaining item with make, model and NSF/UL labels. | Owner | Open
2 | Hood | Get the UL listing and a duct inspection. Replace the roof upblast fan. Install makeup air. Get an NFPA 96 cleaning certificate. | Mechanical contractor | Open
3 | Suppression | Install a new or recertified UL 300 system with fuel shutoff and a K-class extinguisher. | Fire contractor | Open
4 | Sinks | Handwashing sinks, 3-compartment sink, prep sink, mop sink. Check water heater capacity. | Plumber | Open
5 | Grease | Exterior interceptor sized to UPC 2021, with a maintenance schedule filed with the septic design. | Designer / installer | Open
6 | Septic | OSM inspection and flow and strength review. | Certified OSM | Open
7 | Refrigeration and finishes | Refrigeration, thermometers, smooth and cleanable finishes. | Contractor | Open
8 | Plan submittal | Floor plan and menu to Public Health. Set the risk level. | Owner / designer | Open
9 | People | Food worker cards; Certified Food Protection Manager. | Staff | Open
10 | Inspection | Preoperational inspection; operating permit posted. | Owner | Open

## Critical Path
Critical path: kitchen and liquor (weeks from today)
Estimates from the research. Change the target open week and the LCB lead time to see the liquor filing window move.
| Target open week (assumption, midpoint of 24 to 32) | 28
| LCB lead time in weeks (90 days is about 13) | 13
# | Activity | Start wk | End wk | Weeks | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
1 | Records requests, zoning letter, septic inspection, equipment inventory, LLC and UBI | 0 | 4 | 4 | 1 | 1 | 1 | 1
2 | Hood, fan and makeup air design; septic and grease design; Public Health plan submittal | 4 | 12 | 8 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Permits issued: mechanical, fire, plumbing, OSS | 8 | 20 | 12 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | Construction | 12 | 28 | 16 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | LCB application window (file about 90 days before target open) | 15 | 28 | 13 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Finals, Public Health preoperational inspection, LCB approval, open | 24 | 32 | 8 | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Rooms-only go-live window (low to high, from the Rooms Only tab) | 3 | 8 | 5 |  |  |  | 1 | 1 | 1 | 1 | 1
Likely bottlenecks
Septic and grease redesign can add months and dominate cost.
Hood recertification without documents.
King County permit queue before the 2024 code switch on May 3, 2027.
LCB timing stretches if the floor plan, funding or premises documents are incomplete.

## Costs
Cost estimates (low and high)
Blank cells are unknown, not zero. Totals exclude them and the count below each total says how many are missing. Set Include to 0 to drop a line.
Item | Section | Include (1/0) | Low ($) | High ($) | Basis | Note
Records copies | Rooms | 1 |  |  | Unknown | Get from KC Permitting Records Center.
Zoning and Historical Certification Letter | Rooms | 1 |  |  | Unknown | Per 2026 KC fee schedule; confirm with DLS.
WA business license application | Rooms | 1 | 50 | 50 | WAC 458-02-200 | Non-refundable.
Liability insurance or platform coverage | Rooms | 1 |  |  | Unknown | Get a quote. RCW 64.37 requires $1M or equivalent.
Smoke and CO alarms, extinguishers | Rooms | 1 | 100 | 600 | My planning estimate | Verify against what the rooms already have.
Public Health plan review and permit | Kitchen and alcohol | 1 | 1764 | 2500 | PHSKC 2026 | $1,008 plan review plus $756 Risk 2 permit as the low end.
LCB annual license | Kitchen and alcohol | 1 | 600 | 2700 | LCB 2026 | Beer/wine $600; spirits, beer and wine up to $2,700.
Hood fan, makeup air, duct | Kitchen and alcohol | 1 | 8000 | 60000 | Estimate | Widest range because there are no documents.
UL 300 suppression | Kitchen and alcohol | 1 | 3000 | 8000 | Estimate
Grease interceptor (exterior) | Kitchen and alcohol | 1 | 8000 | 30000 | Estimate
Septic upgrade, if required | Kitchen and alcohol | 1 | 0 | 150000 | Estimate | Could be zero or the biggest line.
King County permits: mechanical, fire, building | Kitchen and alcohol | 1 | 2000 | 15000 | Estimate | Check the 2026 fee schedule.
Design: architect, engineer, OSS designer | Kitchen and alcohol | 1 | 5000 | 40000 | Estimate
Totals
Section |  |  | Low ($) | High ($) | Items with no number yet
Rooms |  |  | 150 | 650 | 3
Kitchen and alcohol |  |  | 28364 | 308200 | 0
Everything |  |  | 28514 | 308850 | 3

## Open Questions
Open questions and records requests
Each one narrows a risk in the other tabs. Status is yours to edit.
# | Question or record | Where to ask | Why it matters | Status
1 | King County permit history: original 1993 permit, Certificate of Occupancy, occupancy class, expired permits, code enforcement cases | KC Permitting Records Center (online request) | Shows whether nightly lodging for the rooms is already a permitted use. Decides the rooms-only timeline. | Open
2 | Public Health food permit and inspection history, and the last closure date | PHSKC | The closure date sets the 365-day status that triggers a full plan review. | Open
3 | OSS as-built and design flow | PHSKC online OSS records search | Tells you what the septic can handle before you design a restaurant around it. | Open
4 | LCB license history at the address (Lucy's Table about 2017 to 2018; a 2022 Burton Inn, Spa and Grill listing) | LCB public records | Prior licensee issues or conditions on the premises. | Open
5 | Landlord (J.T. Sheffield LLC): lease use clause, consent to the liquor license, roof fan removal history, who pays for septic and hood work | Landlord and your attorney | Cost allocation and whether the lease permits lodging, a bar and a kitchen. | Open
6 | Exact zoning, P-suffix text, whether hotel/motel or B&B is allowed, and any resident-operator condition | KC DLS zoning letter | Could change the whole lodging plan. | Open
7 | Parcel number: the one LoopNet page found lists 24012 Vashon Hwy SW, not 24007 | KC parcel viewer | Every lookup depends on the right parcel. | Open
8 | Water purveyor and backflow requirements | Burton Water Co-op (verify) | Commercial kitchens often need premises isolation. | Open
9 | Does King County require Fire Marshal operational permits for the restaurant? | KC Fire Marshal | Adds an annual cost and inspection. | Open
10 | Guest cap: 10 or 16 | You | Decides R-3 versus R-1 and the fire and egress scrutiny. | Open
11 | Target hours and seat count (assumed about 40) | You | Fifty or more occupants makes the dining room A-2. | Open
12 | Alcohol path and structure: Burton Inn LLC as licensee, or an operator subleasing | You and your attorney | Drives the entire LCB tab. | Open

## Sources
Sources
Official means a government or agency site. Secondary means verify before relying on it. Retrieved during research on Oct 13, 2026.
# | Publisher | Reliability | URL
1 | LoopNet | Secondary, verify | https://www.loopnet.com/property/24012-vashon-hwy-sw-vashon-wa-98070/53033-1922039014/
2 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/depts/local-services/director/subarea-plans/vashon-maury-island/vashon-subarea-plan-20200724.pdf?rev=bf6f142d42f440a8aab166d3e3caa3f3&hash=6F9B6AD55BEDC8CF66088F721C6FD48C
3 | King County | Official | https://aqua.kingcounty.gov/council/clerk/OldOrdsMotions/Ordinance%2007870.pdf
4 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/independent/governance-and-leadership/government-oversight/hearing-examiner/documents/decisions-recommendations/appeals/code-enforcement/2023/enfr210581_hu.pdf?rev=9340a4d4514745b7b2b7aa68afb29081&hash=F5E52C7715FDF24D86555F0B124CCE33
5 | Vashon-Maury Island Beachcomber | Local news | https://www.vashonbeachcomber.com/news/burton-landmark-purchased-by-island-business/
6 | NeighborWho | Secondary, verify | https://www.neighborwho.com/Vashon-Hwy-Vashon-WA-addresses/
7 | Wikipedia | Secondary, verify | https://en.wikipedia.org/wiki/List_of_landmarks_in_King_County,_Washington
8 | Vashon Sewer District | Official | https://www.vashonsewerdistrict.org/
9 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/depts/dph/documents/about-public-health/board-of-health/boh-code-title-13.pdf
10 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/depts/dph/documents/health-safety/environmental-health/training/septic-system-maintenance-food-establishments.pdf?hash=C23129672BA7905C3CBAE0ED885051C1&rev=ef12098f6bbe4e50a535ff7a46e3455e
11 | WA State Building Code Council | Official | https://sbcc.wa.gov/sites/default/files/2024-02/2021%20IBC%20Insert%20Pages%202nd%20printing.pdf
12 | WA State Building Code Council | Official | https://sbcc.wa.gov/
13 | WA Liquor and Cannabis Board | Official | https://lcb.wa.gov/sites/default/files/2026-01/01-07-2026-5ACR103-LEG-IMPL-PACKAGE-HB1636-1698-2SSB5786.pdf
14 | King County | Official | https://kingcounty.gov/en/dept/local-services/certificates-permits-licenses/permits/permits-inspections-codes-buildings-land-use/permit-forms-application-materials/building-land-use
15 | King County | Official | https://aqua.kingcounty.gov/council/clerk/code/24-30_Title_21A.htm
16 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/depts/local-services/permits/regional-planning/2016compplanupdate/2022execrecommendto2016/2022-0162-area-landuse-and-zoning-studies-kccp_0322.pdf?rev=0ec9cbd0db1f4d7b8ce647a34c1fd328&hash=EE7D6DB7317E12A81D1A93B1100E2FC8
17 | Rexmont | Secondary, verify | https://rexmont.com/short-term-rental-rules-seattle-eastside
18 | King County | Official | https://mkcclegisearch.kingcounty.gov/LegislationDetail.aspx?ID=6195438&GUID=8A026AD2-2871-4729-A611-E266ED8F80A8&Options=Advanced&Search=&FullText=1
19 | Crestcove | Secondary, verify | https://www.crestcove.co/post/vashon-island-str-investment-2026
20 | STR Profit Map | Secondary, verify | https://www.strprofitmap.com/regulations/WA/vashon
21 | WA Legislature | Official | https://app.leg.wa.gov/RCW/default.aspx?cite=64.37&full=true
22 | WA Legislature | Official | https://lawfilesext.leg.wa.gov/law/wsr/2026/10/26-10-068.htm
23 | WA Dept of Health | Official | https://ccwa.doh.wa.gov/search/15338f22-0d4e-5f65-910e-0d6ad7b666ca
24 | Vashon Island Fire & Rescue | Official | https://vifr.org/king-county-fire-marshal-issues-stage-1-burn-ban-restricting-yard-debris-fires-in-unincorporated-areas/
25 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/depts/dph/documents/certificates-permits-licenses/food-worker-business-permits/permanent-businesses/tip-sheet-food-plan-review-application.pdf?rev=e33c2f1fa63d49bbbb5fa4618bf5da9b&hash=893952EEBFC4E35A1CCCF112635BD750
26 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/depts/dph/documents/certificates-permits-licenses/food-worker-business-permits/application-permanent-plan-review.pdf?rev=bddef9971ed847f4ba07ca5107028072&hash=015AC97E4F2EF362E7F83F16990D9CE0
27 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/depts/dph/documents/certificates-permits-licenses/food-worker-business-permits/permanent-businesses/plan-guide-food-service-plan-review.pdf?rev=53032abdb9c14a9291288b286a679bca&hash=F97AD0417B8768A63B0B0B4F0FC9FA67
28 | King County | Official | https://cdn.kingcounty.gov/-/media/king-county/depts/dph/documents/health-safety/environmental-health/fees/food-establishment-fees-through-2026.pdf?rev=09ce3ebf747f42638de9b1c4aebfd151&hash=95431ACD5356F5C13071CCBC053B54A8
29 | King County | Official | https://kingcounty.gov/en/-/media/king-county/depts/dph/documents/certificates-permits-licenses/food-worker-business-permits/food-service-plan-submittal-tip-sheet.pdf
30 | WA Liquor and Cannabis Board | Official | https://lcb.wa.gov/sites/default/files/publications/licensing/Liquor-Retail-Licensing-Guide.pdf
31 | WA Liquor and Cannabis Board | Official | https://lcb.wa.gov/content/phase-1-getting-started-your-liquor-license-application
32 | WA Liquor and Cannabis Board | Official | https://lcb.wa.gov/llg/licensing_process
33 | WA Liquor and Cannabis Board | Official | https://lcb.wa.gov/enforcement/faqs
34 | CityRuleLookup | Secondary, verify | https://cityrulelookup.com/counties/king-county-wa/rental-property
35 | BnbCalc | Secondary, verify | https://www.bnbcalc.com/blog/short-term-rental-regulation/King-County-Washington-Guide
36 | Stay Flourish | Secondary, verify | https://stayflourish.com/short-term-rental-taxes-washington.html
37 | WA Dept of Revenue | Official | https://dor.wa.gov/forms-publications/publications-subject/tax-topics/airbnb-collect-and-send-taxes-behalf-hosts
38 | Avalara | Secondary, verify | https://www.avalara.com/mylodgetax/en/blog/2018/10/taxes-rise-on-short-term-rentals-in-king-county-washington.html
39 | Valta Realty | Secondary, verify | https://valtarealty.com/blog/vacation-rental-taxes-washington
40 | WA Legislature | Official | https://app.leg.wa.gov/wac/default.aspx?cite=314-02-035
41 | WA Liquor and Cannabis Board | Official | https://lcb.wa.gov/licensing/retail_liquor_and_endorsement_description_and_fees_info
42 | WA Legislature | Official | https://lawfilesext.leg.wa.gov/biennium/2025-26/Pdf/Bill%20Reports/House/2536%20HBA%20CPB%2026.pdf
43 | WA Liquor and Cannabis Board | Official | https://lcb.wa.gov/licensing/special-licenses-and-permits
44 | King County | Official | https://kingcounty.gov/en/dept/local-services/buildings-property/public-notices-permit-records-search/permit-records-research
45 | Vashon-Maury Island Beachcomber | Local news | https://www.vashonbeachcomber.com/news/burton-inn-is-once-again-on-the-market/
46 | Facebook (Burton Inn page) | Secondary, verify | https://www.facebook.com/BurtonInnVashon/
Note: the one LoopNet page found is for 24012 Vashon Hwy SW. The zoning and size data attributed to 24007 in the research need a parcel check.